## Individual Timesheets for all s
Week | Student ID | Name | Hours [1- 6] | Activity details
Week 03 | S394695 | Amsh Shrestha | 1 | Research multiple issues faced by people on technological area
Week 03 | S394695 | Amsh Shrestha | 1 | Identified the most suitable candidate:splitsync
Week 03 | S394695 | Amsh Shrestha | 1 | Did analysis on alternatives/competitors, their strength and weakness
Week 03 | S394695 | Amsh Shrestha | 1 | Created canvas on how we will build the application and what will be different from competitors
Week 03 | S394695 | Amsh Shrestha | 0.5 | Held a meeting to present the idea to decide to progress, merge or discard the idea
Week 03 | S394695 | Amsh Shrestha | 0.5 | Finalised the project
Week 03 | S394695 | Amsh Shrestha | 0
Week 04 | S394695 | Amsh Shrestha | 0.5 | Updated trello about tasks to perform in week 04
Week 04 | S394695 | Amsh Shrestha | 1 | Designed SplitSync wireframe layouts: onboarding and balance dashboard
Week 04 | S394695 | Amsh Shrestha | 1 | Designed SplitSync wireframe layouts : bill setup and bill detail screens
Week 04 | S394695 | Amsh Shrestha | 1 | Designed SplitSync wireframe layouts: payment confirmation and notifications
Week 04 | S394695 | Amsh Shrestha | 0.5 | Created Kinde Account and Test Keys
Week 04 | S394695 | Amsh Shrestha | 0.5 | Scaffold PWA react and .net monorepos
Week 04 | S394695 | Amsh Shrestha
Week 05 | S394695 | Amsh Shrestha | 3 | Built authentication backend: ASP.NET Core Identity, JWT issuance, register/login by email or username, EF Core + SQLite migration
Week 05 | S394695 | Amsh Shrestha | 1.5 | Built homepage and profile pages in React frontend
Week 05 | S394695 | Amsh Shrestha | 1.5 | Resolved git rebase conflict merging authentication work with teammates' changes; verified build and tests passed
Week 06 | S394695 | Amsh Shrestha | 3 | Built group feature backend: Group + GroupMember models, GroupsController (create/list/add-member/join-by-ID endpoints), migration applied to Supabase
Week 06 | S394695 | Amsh Shrestha | 2 | Built GroupsPage frontend: create/list/join groups, per-group add-member form, wired to real API
Week 06 | S394695 | Amsh Shrestha | 0.5 | Removed unused Continue with Google sign-in stub from AuthenticationPage
Week 06 | S394695 | Amsh Shrestha | 0.5 | Git workflow troubleshooting: resolved commit message quoting issue